## Milestones
Phase | Owner | Milestone | Definition of done | Status
Plan | Whole team | Read brief + lock data contract | docs/data-contract.md agreed | Done
Plan | Whole team | Roles + Scrum Master assigned | Names in docs/team-ownership.md | Not Started
Build | JD Analytics | Role 1 | Extract skills from 2+ sample JDs | In Progress
Build | Resume Parsing | Role 2 | Parse 2+ sample resumes | Done
Build | Profile Builder | Role 3 | Save/load profile + CV upload | Done
Build | Talent Check | Role 4 | Score differs per candidate | Done
Build | Skill Matching | Role 5 | Match score + gap list on 2+ JDs | Done
Integrate | Whole team | 5 pieces wired end to end | 1 company/JD/candidate runs fully | In Progress
Prepare | Whole team | Rehearsed live demo | Run without mentor help | Not Started